## Sheet1
Iteration | User Stories | Tasks | Difficulty/Estimate | Status | Owner | Description
Iteration 0 Deadline Feb 6 | Development Setup | Setup Jenkins CI system | Hard | Complete | Brandon
|  | Setup rails environment | Medium |  | Everyone | Install Aptana, Ruby, Rails.
Iteration 1 Deadline Feb 26 | Administrator is able to maintain users | Setup user access control | Hard |  |  | Investigate available ruby autentication plugins, setup base user access control.
|  | User control for administrator | Medium |  |  | Create administrator page that has administrator specific behaviour.
|  | Admin can manage users | Medium |  |  | Administrators will be able to add, delete, search, and modify user accounts.
|  | User permissions | Hard |  |  | Adminstrators will be able to manage the permissions of other users and roles.
| Users are able to login to the system. | User control for sales associates | Easy
|  | User control for hotel managers | Easy
|  | User control for registered customers | Easy
| Customer information management | Sales associates can manage customers | Hard |  |  | Sales associates will be able to add, delete, and modify customers.
|  | Sales associates can search for specific customers | Hard |  |  | Sales associates will be able to do a very simple search of the customers by the customer name.
Iteration 2 Deadline Mar 19 | Hotel management | Administrators can manage hotels | Hard |  |  | Administrators will be able to add, delete, and modify hotels.
|  | Users can search hotels | Hard |  |  | Users will be able to search hotels
| Room management | Hotel managers can manage rooms | Medium |  |  | Hotel managers will be able to add, delete, and modify rooms.
|  | Hotel managers can manage room types | Easy |  |  | Hotel managers will be able to add, delete, and modify room types.
|  | Sales associates can view the list of rooms | Medium |  |  | Sales associates will be able to do a very simple search of the rooms.
| Room booking and management | Sales associates can manage room bookings | Hard |  |  | Sales associates will be able to add, delete, and modify room bookings.
|  | Sales associates can view bookings | Medium |  |  | Sales associates will be able to search for room bookings.
Iteration 3 Deadline Apr 9 | Invoicing | Sales associates can record customer payments | Hard |  |  | Sales associates will be able to record customer payments and manage invoicing status.
|  | Sales associates can view customer billing history | Medium |  |  | Sales associates will be able to view customer billing history.
| Room service | User control for room service | Easy
|  | Room service can view customers by room number | Medium |  |  | Room service associates will be able to view customers by room number.
|  | Room service can manage the room service bill | Medium |  |  | Room service associates will be able to add, delete, and modify the room service bill for customers at their hotel.
| Customer self-service | New customers can register to the system | Hard |  |  | Customers should be able to register with the system if they do not already have an account.
|  | User control for customers | Easy
|  | Customers can view available rooms | Easy |  |  | Registered customers will be able to view the available rooms.
|  | Customers can manage their room bookings | Easy |  |  | Registered customers will be able to book rooms, remove reservations, and view their current reservations and payment history.
Iteration 4 Deadline May 1 | Trouble ticket management | Customers can issue trouble tickets | Hard |  |  | Customers should be able to issue trouble tickets which can be managed by hotel workers.
|  | Sales associates can resolve trouble tickets | Hard |  |  | Sales associates should be able to view and manage trouble tickets, including responding and resolving issues.
| Housekeeping | User control for housekeeping | Easy
|  | House keeping can manage cleanliness status | Hard |  |  | House keeping should be able to view room cleanliness status and mark rooms as cleaned, as well as view the rooms they are responsible for.
| Reporting | Hotel managers can produce reports on accounts receivable, hotel utilization, etc. | Hard |  |  | Hotel managers should be able to view and manage reports on the hotel's accounts receivable, view the hotel utilization, view the average rate where customers do not show up, view and suspend delinquent accounts, etc.